## DOT
SUMMONS & VIOLATIONS TRACKING
AGENCY | VIOLATION NO. | VIOLATION DATE | CODE VIOLATION | VIOLATION DESCRIPTION | BORO | PLACE OF OCCURRENCE | JOB NO. | MAIL-IN PENALTY | MAX PENALTY | HEARING DATE | BIC | COMMENTS | IMPOSED PENALTY | DATE PAID | AMOUNT PAID
NYCDOT | 0703792522 | 2025-01-07 14:32 | 34 RCNY 2-11(e)(10)(v) | Failure to countersink plates flush with roadway (DR5) | BRONX | 775 EAST 183 STREET Btwn PROSPECT AVENUE and BOROUGH: BRONX SOUTHERN BOULEVARD | LSLRPBX2 | 1000 | 3000 | 2025-04-14 08:30 | Robert Ligansky | Penalty Imposed | 1000
NYCDOT | 0703792513 | 2025-01-07 14:43 | 34 RCNY 2-11(e)(10)(v) | Failure to post “Steel Plates Ahead” or “Raise Plow” sign (D70) | BRONX | 775 EAST 183 STREET Btwn PROSPECT AVENUE and BOROUGH: BRONX SOUTHERN BOULEVARD | LSLRPBX2 | 500 | 1500 | 2025-04-14 08:30 | Robert Ligansky | Dismissed | 0
NYCDOT | 0703792504 | 2025-01-07 15:15 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BRONX | 2354 PROSPECT AVENUE Btwn EAST 185 STREET and EAST 187 STREET | LSLRPBX2 | 1200 | 3600 | 2025-04-14 08:30 | Robert Ligansky | Penalty Imposed | 1200
NYCDOT | 0703792569 | 2025-01-07 15:32 | 34 RCNY 2-11(e)(4)(v) | Failure to post flagperson at worksite to give directions (D5E) | BRONX | 2354 PROSPECT AVENUE Btwn EAST 185 STREET and EAST 187 STREET | LSLRPBX2 | 800 | 2400 | 2025-04-14 08:30 | Robert Ligansky | Dismissed | 0
NYCDOT | 0703802588 | 2025-01-21 13:08 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | 6 AVENUE and DEAN STREET | SEK002383 | 1200 | 3600 | 2025-05-01 08:30 | Robert Ligansky | Plates are countersunk and ramped. | 0
NYCDOT | 0703801607 | 2025-01-21 13:17 | 34 RCNY 2-11(e)(10)(v) | Failure to post “Steel Plates Ahead” or “Raise Plow” sign (D70) | BROOKLYN | 6 AVENUE and DEAN STREET | SEK002383 | 500 | 1500 | 2025-05-01 08:30 | Robert Ligansky | Plates are countersunk and ramped. | 500
NYCDOT | 0703801533 | 2025-01-21 08:08 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1200 | 3600 | 2025-05-01 08:30 | Robert Ligansky |  | 1200
NYCDOT | 0703802606 | 2025-01-21 12:57 | 34 RCNY 2-11(e)(10)(viii) | Failure to add required identifying information to plating and decking | BROOKLYN | 6 AVENUE and DEAN STREET | SEK002383 | 250 | 500 | 2025-05-01 08:30 | Robert Ligansky |  | 250
NYCDOT | 0703810791 | 2025-02-02 16:52 | 34 RCNY 2-02(c)(4) | Failure to have the necessary ID markings on DOT required signs. (DG3) | MANHATTAN | VESEY STREET Btwn ANN STREET and CHURCH STREET | SUMMONS & VIOLATIONS TRACKING | 750 | 2250 | 2025-05-12 08:30 | Robert Ligansky | Reduced during at Hearing | 100
NYCDOT | 0703813330 | 2025-02-05 13:54 | 34 RCNY 2-02(c)(4) | Failure to have the necessary ID markings on DOT required signs. (DG3) | BROOKLYN | 6 AVENUE and DEAN STREET | SEK002383 | 750 | 2250 | 2025-05-15 08:30 | Robert Ligansky | Reduced during at Hearing | 100
NYCDOT | 0703813514 | 2025-02-05 13:50 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | 6 AVENUE and DEAN STREET | SEK002383 | 1200 | 3600 | 2025-05-15 08:30 | Robert Ligansky | Plates were countersunk & pinned. See DeBoe pics. Reduced at Hearing | 500
NYCDOT | 0703817456 | 2025-02-05 10:19 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | QUEENS | 212 PLACE Btwn 104 ROAD and HOLLIS AVENUE | SEQS24 | 1500 | 5000 | 2025-05-14 08:30 | Robert Ligansky | Reduced during at Hearing | 750
NYCDOT | 0703851455 | 2025-03-10 12:18 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | BRONX | CAMBRELENG AVENUE Btwn EAST 188 STREET and BOROUGH: BRONX EAST 189 STREET | LSLRPBX2 | 1500 | 5000 | 2025-06-16 08:30 | Dane |  | 1530
NYCDOT | 0703852876 | 2025-04-01 08:51 | 34 RCNY 2-11(e)(16)(iii) | Failure to comply with all applicable sections of the Highway Rules, the | BROOKLYN | DOVER STREET Btwn HAMPTON AVENUE and ORIENTAL BOULEVARD | BED819 | 750 | 1000 | 2025-07-10 08:30 | Dane
NYCDOT | 0703860951 | 2025-04-06 15:33 | 0137P; 12787; 34 RCNY 2-02(d)(2); CT - 6; WORK 7AM; WORK 9AM; o Q012024325B10 (0137P); o Q012024325B11 (0137P); o Q012024325B12 (0137P); o Q012024325B13 (0137P); o Q012024325B14 (0137P); o Q012024325B15 (0137P); o Q012024328A06 (0137P) | 4PM, MONDAY TO FRIDAY ¦ 6PM, MONDAY TO FRIDAY ¦ DEBOE CONSTRUCTION CORP. ¦ DEP CONTRACTOR MAJOR INSTALLATION ¦ ELKS COURT HUNTINGTON NY 11743 ¦ Failure to obtain proper permits to repair the conditions reported on a CAR. ¦ Issued Date: 11/20/2024 - Location: 114 Road, 225th Street to 226th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 226th Street to 227th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 227th Street to Cross ¦ Issued Date: 11/23/2024 - Location: 114 Road, Cross Island Parkway | QUEENS | 114 ROAD and 226 STREET | SEQS24 | 500 | 1500 | 2025-07-16 08:30 | Dane | Dismissed | 0
NYCDOT | 0703860960 | 2025-04-06 15:31 | 0137P; 12787; 34 RCNY 2-02(d)(2); CT - 6; WORK 7AM; WORK 9AM; o Q012024325B10 (0137P); o Q012024325B11 (0137P); o Q012024325B12 (0137P); o Q012024325B13 (0137P); o Q012024325B14 (0137P); o Q012024325B15 (0137P); o Q012024328A06 (0137P) | 4PM, MONDAY TO FRIDAY ¦ 6PM, MONDAY TO FRIDAY ¦ DEBOE CONSTRUCTION CORP. ¦ DEP CONTRACTOR MAJOR INSTALLATION ¦ ELKS COURT HUNTINGTON NY 11743 ¦ Failure to obtain proper permits to repair the conditions reported on a CAR. ¦ Issued Date: 11/20/2024 - Location: 114 Road, 225th Street to 226th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 226th Street to 227th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 227th Street to Cross ¦ Issued Date: 11/23/2024 - Location: 114 Road, Cross Island Parkway | QUEENS | 114 ROAD Btwn 225 STREET and 226 STREET | SEQS24 | 500 | 1500 | 2025-07-16 08:30 | Dane | Dismissed | 0
NYCDOT | 0703860989 | 2025-04-06 15:24 | 0137P; 12787; 34 RCNY 2-02(d)(2); CT - 6; WORK 7AM; WORK 9AM; o Q012024325B10 (0137P); o Q012024325B11 (0137P); o Q012024325B12 (0137P); o Q012024325B13 (0137P); o Q012024325B14 (0137P); o Q012024325B15 (0137P); o Q012024328A06 (0137P) | 4PM, MONDAY TO FRIDAY ¦ 6PM, MONDAY TO FRIDAY ¦ DEBOE CONSTRUCTION CORP. ¦ DEP CONTRACTOR MAJOR INSTALLATION ¦ ELKS COURT HUNTINGTON NY 11743 ¦ Failure to obtain proper permits to repair the conditions reported on a CAR. ¦ Issued Date: 11/20/2024 - Location: 114 Road, 225th Street to 226th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 226th Street to 227th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 227th Street to Cross ¦ Issued Date: 11/23/2024 - Location: 114 Road, Cross Island Parkway | QUEENS | 114 ROAD and 227 STREET | SEQS24 | 500 | 1500 | 2025-07-16 08:30 | Dane | Dismissed | 0
NYCDOT | 0703861007 | 2025-04-06 15:18 | 0137P; 12787; 34 RCNY 2-02(d)(2); CT - 6; WORK 7AM; WORK 9AM; o Q012024325B10 (0137P); o Q012024325B11 (0137P); o Q012024325B12 (0137P); o Q012024325B13 (0137P); o Q012024325B14 (0137P); o Q012024325B15 (0137P); o Q012024328A06 (0137P) | 4PM, MONDAY TO FRIDAY ¦ 6PM, MONDAY TO FRIDAY ¦ DEBOE CONSTRUCTION CORP. ¦ DEP CONTRACTOR MAJOR INSTALLATION ¦ ELKS COURT HUNTINGTON NY 11743 ¦ Failure to obtain proper permits to repair the conditions reported on a CAR. ¦ Issued Date: 11/20/2024 - Location: 114 Road, 225th Street to 226th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 226th Street to 227th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 227th Street to Cross ¦ Issued Date: 11/23/2024 - Location: 114 Road, Cross Island Parkway | QUEENS | 114 ROAD Btwn 226 STREET and 227 STREET | SEQS24 | 500 | 1500 | 2025-07-16 08:30 | Dane | Dismissed | 0
NYCDOT | 0703861016 | 2025-04-06 15:04 | 0137P; 12787; 34 RCNY 2-02(d)(2); CT - 6; WORK 7AM; WORK 9AM; o Q012024325B10 (0137P); o Q012024325B11 (0137P); o Q012024325B12 (0137P); o Q012024325B13 (0137P); o Q012024325B14 (0137P); o Q012024325B15 (0137P); o Q012024328A06 (0137P) | 4PM, MONDAY TO FRIDAY ¦ 6PM, MONDAY TO FRIDAY ¦ DEBOE CONSTRUCTION CORP. ¦ DEP CONTRACTOR MAJOR INSTALLATION ¦ ELKS COURT HUNTINGTON NY 11743 ¦ Failure to obtain proper permits to repair the conditions reported on a CAR. ¦ Issued Date: 11/20/2024 - Location: 114 Road, 225th Street to 226th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 226th Street to 227th ¦ Issued Date: 11/20/2024 - Location: 114 Road, 227th Street to Cross ¦ Issued Date: 11/23/2024 - Location: 114 Road, Cross Island Parkway | QUEENS | 114 ROAD Btwn 227 STREET and CROSS ISLAND PARKWAY | SEQS24 | 500 | 1500 | 2025-07-16 08:30 | Dane | Dismissed | 0
NYCDOT | 0703908958 | 2025-05-31 10:33 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | BRONX | 2251 HUGHES AVENUE Btwn CRESCENT AVENUE and EAST 183 STREET | LSLRPBX2 | 1500 | 5000 | 2025-09-08 08:30 | Dane
NYCDOT | 0703908967 | 2025-05-31 11:03 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | BRONX | 2244 HUGHES AVENUE Btwn CRESCENT AVENUE and EAST 183 STREET | LSLRPBX2 | 1500 | 5000 | 2025-09-08 08:30 | Dane
NYCDOT | 0703922369 | 2025-06-16 15:18 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 227 STREET and CROSS ISLAND PARKWAY | SEQS24 | 500 | 1500 | 2025-09-24 08:30 | Dane | DISMISSED
NYCDOT | 0703922414 | 2025-06-16 15:26 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 226 STREET and 227 STREET | SEQS24 | 500 | 1500 | 2025-09-24 08:30 | Dane | DISMISSED
NYCDOT | 0703922432 | 2025-06-16 15:36 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 225 STREET and 226 STREET | SEQS24 | 500 | 1500 | 2025-09-24 08:30 | Dane | DISMISSED
NYCDOT | 0703922441 | 2025-06-16 15:31 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD and 226 STREET | SEQS24 | 500 | 1500 | 2025-09-24 08:30 | Dane | DISMISSED
NYCDOT | 0703922460 | 2025-06-16 15:22 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD and 227 STREET | SEQS24 | 500 | 1500 | 2025-09-24 08:30 | Dane | DISMISSED
NYCDOT | 0703967743 | 2025-08-05 14:29 | 34 RCNY 2-02(c)(4) | Failure to have the necessary ID markings on DOT required signs. (DG3) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 750 | 2250 | 2025-11-13 08:30 | Robert Ligansky
NYCDOT | 0703968641 | 2025-08-07 12:54 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1200 | 3600 | 2025-11-13 08:30 | Robert Ligansky | OATH Decision
NYCDOT | 0703986250 | 2025-08-24 12:10 |  | Failure to provide temporary bike lane around work area |  | Dean St b/w 6 Ave & Carlton Ave, Brooklyn | SEK002383 | 1200 | 3600 | 2025-12-04 08:30 | Robert Ligansky
NYCDOT | 0703995005 | 2025-09-05 08:42 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | RIVERDALE AVENUE Btwn NEW JERSEY AVENUE and BOROUGH: BROOKLYN VERMONT STREET | SEKS25 | 1200 | 3600 | 2025-12-11 08:30 | Dane
NYCDOT | 0703995041 | 2025-09-05 08:51 | (WORK 9AM; A.C. 19-102(ii) | 2PM, MONDAY TO FRIDAY) THIS PERMIT IS NOT A EMERGENCY. RESPONDENT FAILED TO ¦ Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | RIVERDALE AVENUE Btwn NEW JERSEY AVENUE and BOROUGH: BROOKLYN PENNSYLVANIA AVENUE | SEKS25 | 1200 | 3600 | 2025-12-11 08:30 | Dane
NYCDOT | 0703999982 | 2025-09-10 15:02 | 34 RCNY 2-11(g)(2)(i) | Failure to begin emergency work within 2 hours after authorization (D6E) | BROOKLYN | COZINE AVENUE and FORBELL STREET | SEKS25 | 1000 | 3000 | 2025-12-18 08:30 | Dane
NYCDOT | 0704000404 | 2025-09-05 14:31 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2025-12-11 08:30 | Robert Ligansky
NYCDOT | 0704000395 | 2025-09-05 14:19 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1200 | 3600 | 2025-12-11 08:30 | Robert Ligansky
NYCDOT | 0704010432 | 2025-09-20 14:28 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2025-12-18 08:30 | Robert Ligansky
NYCDOT | 0704012760 | 2025-09-26 18:21 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | BROOKLYN | NEW JERSEY AVENUE Btwn BEND and RIVERDALE AVENUE | SEKS25 | 1500 | 5000 | 2026-01-08 08:30 | Dane
NYCDOT | 0704014448 | 2025-09-23 16:26 |  | Failre to Obtain permits to repair CAR |  | 114 Rd btwn 227 St & Cross Island | SEQS24 | 500 | 1500 | 2025-12-31 08:30 | Dane | CASE ALREADY DISMISSED - JUDGEMENT TO BE CONTESTED
NYCDOT | 0704014410 | 2025-09-23 16:27 |  | Failre to Obtain permits to repair CAR |  | 114 Rd btwn 225 St & 226 St | SEQS24 | 500 | 1500 | 2025-12-31 08:30 | Dane | CASE ALREADY DISMISSED - JUDGEMENT TO BE CONTESTED
NYCDOT | 0704014420 | 2025-09-23 16:27 |  | Failre to Obtain permits to repair CAR |  | 114 Rd btwn 226 St & 227 St | SEQS24 | 500 | 1500 | 2025-12-31 08:30 | Dane | CASE ALREADY DISMISSED - JUDGEMENT TO BE CONTESTED
NYCDOT | 0704014392 | 2025-09-23 16:37 |  | Failre to Obtain permits to repair CAR |  | 114 Rd and 226 St | SEQS24 | 500 | 1500 | 2025-12-31 08:30 | Dane | CASE ALREADY DISMISSED - JUDGEMENT TO BE CONTESTED
NYCDOT | 0704014401 | 2025-09-23 16:36 |  | Failre to Obtain permits to repair CAR |  | 114 Rd and 227 St | SEQS24 | 500 | 1500 | 2025-12-31 08:30 | Dane | CASE ALREADY DISMISSED - JUDGEMENT TO BE CONTESTED
NYCDOT | 0703874629 | 2025-04-23 12:49 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | QUEENS | NEWBURG STREET and QUENCER ROAD | SEQS24 | 1500 | 5000 | 2025-07-30 08:30 | Robert Ligansky
NYCDOT | 0703874638 | 2025-04-23 11:48 | A.C. 19-102(i) | Use/opening of street without DOT permit (D01) | QUEENS | QUENCER ROAD Btwn MEXICO STREET and NEWBURG STREET | SEQS24 | 1500 | 5000 | 2025-07-30 08:30 | Robert Ligansky
NYCDOT | 0703914229 | 2025-05-10 07:59 | 34 RCNY 2-11(e)(16)(iii) | Failure to comply with all applicable sections of the Highway Rules, the | BROOKLYN | DOVER STREET Btwn HAMPTON AVENUE and ORIENTAL BOULEVARD | BED819 | 750 | 1000 | 2025-08-14 08:30 | Robert Ligansky
NYCDOT | 0704045632 | 2025-11-01 10:11 | A.C. 19-147(d) | Failure to replace loose, slippery or broken utility maintenance hole (manhole) | BRONX | 2378 HUGHES AVENUE Btwn EAST 186 STREET and BOROUGH: BRONX EAST 187 STREET | LSLRPBX2 | 250 | 750 | 2026-02-02 08:30 | Dane
NYCDOT | 0705058364 | 2025-11-06 00:59 |  | Failure to pin steel road plate |  | Dean St b/w 6 Ave & Carlton Ave, Brooklyn | SEK002383 | 1200 | 3600 | 2026-02-12 08:30 | Robert Ligansky
NYCDOT | 0705058391 | 2025-11-06 01:14 |  | Failure to identify steel road plate |  | Dean St b/w 6 Ave & Carlton Ave, Brooklyn | SEK002383 | 250 | 500 | 2026-02-12 08:30 | Robert Ligansky
NYCDOT | 0704055541 | 2025-11-13 02:35 | 34 RCNY 2-11(e)(10)(viii) | Failure to add required identifying information to plating and decking | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 250 | 500 | 2026-02-19 08:30 | Robert Ligansky
NYCDOT | 0704055523 | 2025-11-13 02:28 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2026-02-19 08:30 | Robert Ligansky
NYCDOT | 0704059456 | 2025-11-18 16:45 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1200 | 3600 | 2026-02-26 08:30 | Robert Ligansky
NYCDOT | 0704059539 | 2025-11-18 17:22 | A.C. 19-107 | Street closing without DOT permit (D03) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1800 | 5000 | 2026-02-26 08:30 | Robert Ligansky
NYCDOT | 0704068999 | 2025-11-21 08:22 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1200 | 3600 | 2026-02-26 08:30 | Dane
NYCDOT | 0704073637 | 2025-12-03 02:32 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2026-03-12 08:30 | Robert Ligansky
NYCDOT | 0704075680 | 2025-12-05 11:02 | A.C. 19-107 | Street closing without DOT permit (D03) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1800 | 5000 | 2026-03-12 08:30 | Dane
NYCDOT | 0704075679 | 2025-12-05 10:40 |  | Failure to maintain 1-11 Ft Lane | BROOKLYN | 37 St b/w 14 Ave & 15 Ave | SEKS25 | 1200 | 3600 | 2026-03-12 08:30 | Dane | if we have no permits, how can we have stips?
NYCDOT | 0704078266 | 2025-12-08 12:51 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1200 | 3600 | 2026-03-19 08:30 | Dane
NYCDOT | 0704080722 | 2025-12-10 11:00 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1200 | 3600 | 2026-03-19 08:30 | Dane
NYCDOT | 0704079274 | 2025-12-10 11:03 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 225 STREET and 226 STREET | SEQS24 | 500 | 1500 | 2026-03-18 08:30 | Dane | TO BE DISMISSED BECAUSE WE BEAT THIS ALREADY 20 TIMES
NYCDOT | 0704079265 | 2025-12-10 10:25 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD and 226 STREET | SEQS24 | 500 | 1500 | 2026-03-18 08:30 | Dane | TO BE DISMISSED BECAUSE WE BEAT THIS ALREADY 20 TIMES
NYCDOT | 0704079247 | 2025-12-10 10:17 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 226 STREET and 227 STREET | SEQS24 | 500 | 1500 | 2026-03-18 08:30 | Dane | TO BE DISMISSED BECAUSE WE BEAT THIS ALREADY 20 TIMES
NYCDOT | 0704078980 | 2025-12-10 10:07 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD Btwn 227 STREET and CROSS ISLAND PARKWAY | SEQS24 | 500 | 1500 | 2026-03-18 08:30 | Dane | TO BE DISMISSED BECAUSE WE BEAT THIS ALREADY 20 TIMES
NYCDOT | 0704078935 | 2025-12-10 10:14 | 34 RCNY 2-02(d)(2) | Failure to obtain proper permits to repair the conditions reported on a CAR. | QUEENS | 114 ROAD and 227 STREET | SEQS24 | 500 | 1500 | 2026-03-18 08:30 | Dane | TO BE DISMISSED BECAUSE WE BEAT THIS ALREADY 20 TIMES
NYCDOT | 0704082089 | 2025-12-12 11:37 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1200 | 3600 | 2026-03-19 08:30 | Dane
NYCDOT | 0704083490 | 2025-12-12 15:12 | 34 RCNY 2-11(e)(10)(v) | Failure to countersink plates flush with roadway (DR5) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1000 | 3000 | 2026-03-19 08:30 | Dane
NYCDOT | 0704084893 | 2025-12-12 15:16 | 34 RCNY 2-11(e)(10)(viii) | Failure to add required identifying information to plating and decking | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 250 | 500 | 2026-03-19 08:30 | Dane
NYCDOT | 0704084370 | 2025-12-16 01:32 | 34 RCNY 2-11(e)(10)(v) | Failure to countersink plates flush with roadway (DR5) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1000 | 3000 | 2026-03-26 08:30 | Robert Ligansky
NYCDOT | 0704084361 | 2025-12-16 01:12 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2026-03-26 08:30 | Robert Ligansky
NYCDOT | 0704040462 | 2025-10-18 14:35 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 1200 | 3600 | 2026-01-22 08:30 | Joel
NYCDOT | 0704048364 | 2025-11-06 00:59 | 34 RCNY 2-11(e)(10)(iii) | Failure to properly fasten plating and decking (DQ5) | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 1200 | 3600 | 2026-02-12 08:30 | Joel
NYCDOT | 0704048391 | 2025-11-06 01:14 | 34 RCNY 2-11(e)(10)(viii) | Failure to add required identifying information to plating and decking | BROOKLYN | DEAN STREET Btwn 6 AVENUE and CARLTON AVENUE | SEK002383 | 250 | 500 | 2026-02-12 08:30 | Joel
NYCDOT | 0704073646 | 2025-12-03 02:50 | 34 RCNY 2-11(e)(10)(v) | Failure to post “Steel Plates Ahead” or “Raise Plow” sign (D70) | BROOKLYN | DEAN STREET Btwn CARLTON AVENUE and VANDERBILT AVENUE | SEK002383 | 500 | 1500 | 2026-03-12 08:30 | Joel
NYCDOT | 0704075379 | 2025-12-04 10:40 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 37 STREET Btwn 14 AVENUE and 15 AVENUE | SEKS25 | 1200 | 3600 | 2026-03-12 08:30 | Dane
NYCDOT | 0704021661 | 2025-10-01 13:46 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 21 AVENUE and 58 STREET |  | 1200 | 3600 | 2026-01-08 08:30 | Dane
NYCDOT | 0704040509 | 2025-10-24 16:55 | A.C. 19-102(ii) | Failure to comply with terms and conditions of DOT permit (D30) | BROOKLYN | 58 STREET Btwn 21 AVENUE and WASHINGTON CEMETERY BOUNDARY | SEKS25 | 1200 | 3600 | 2026-01-29 08:30 | Dane

## CAR
SUMMONS & VIOLATIONS TRACKING
AGENCY | VIOLATION NO. | VIOLATION DATE | VIOLATION DESCRIPTION | PLACE OF OCCURRENCE | JOB NO. | MAIL-IN PENALTY | MAX PENALTY | HEARING DATE | BIC | COMMENTS | IMPOSED PENALTY | DATE PAID | AMOUNT PAID
NYCDOT CAR | 20245340288-01 | 2025-11-14 | Temporary trench is overdue for final | 114 rd b/w 225 St & 226 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340288-02 | 2025-04-06 | Restored temp trench without obtaining proper permits | 114 rd b/w 225 St & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340288-03 | 2025-06-16 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 rd b/w 225 St & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340288-04 | 2025-09-26 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 rd b/w 225 St & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340288-05 | 2025-12-10 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 rd b/w 225 St & 226 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340289-01 | 2024-11-14 | Intersection of 114 Rd & 226 St temp overdue is Overdue | 114 Rd & 226 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340289-02 | 2025-04-06 | Restored temp trench without obtaining proper permits | 114 Rd & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340289-03 | 2025-06-16 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340289-04 | 2025-09-29 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 226 St | SEQS24 | 40 | 40 | N/A
| 20245340289-05 | 2025-12-10 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 226 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340290-01 | 2024-11-14 | Temp trench from 226 St to 227 St is overdue for final | 114 Rd b/w 226 St & 227 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340290-02 | 2025-04-06 | Restored temp trench without obtaining proper permits | 114 Rd b/w 226 St & 227 St | SEQS24 | 40 | 40 | N/A
| 20245340290-03 | 2025-06-16 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 226 St & 227 St | SEQS24 | 40 | 40 | N/A
| 20245340290-04 | 2025-09-26 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 226 St & 227 St | SEQS24 | 40 | 40 | N/A
| 20245340290-05 | 2025-12-10 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 226 St & 227 St | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340291-01 | 2024-11-14 | Temporary trench is overdue for final | 114 Rd & 227 St intersection | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340291-02 | 2025-04-06 | Restored temp trench without obtaining proper permits | 114 Rd & 227 St intersection | SEQS24 | 40 | 40 | N/A
| 20245340291-03 | 2025-06-16 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 227 St intersection | SEQS24 | 40 | 40 | N/A
| 20245340291-04 | 2025-09-26 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 227 St intersection | SEQS24 | 40 | 40 | N/A
| 20245340291-05 | 2025-12-10 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd & 227 St intersection | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340292-01 | 2024-11-14 | Temp trench from 227 St to Cross Island Pwky is overdue for final | 114 Rd b/w 227 St & Cross Island | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20245340292-02 | 2025-04-06 | Restored temp trench without obtaining proper permits | 114 Rd b/w 227 St & Cross Island | SEQS24 | 40 | 40 | N/A
| 20245340292-03 | 2025-06-16 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 227 St & Cross Island | SEQS24 | 40 | 40 | N/A
| 20245340292-04 | 2025-09-29 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 227 St & Cross Island | SEQS24 | 40 | 40 | N/A
| 20245340292-05 | 2025-12-10 | Failure to obtain proper permits to repair the conditions reported on a CAR | 114 Rd b/w 227 St & Cross Island | SEQS24 | 40 | 40 | N/A
NYCDOT CAR | 20248520371-01 | 2024-11-13 | Curb IFO 186 Dover St broken by heavy equipment. | Dover St b/w Hampton Ave & Oriental Blvd | BED819 | 40 | 40 | N/A
NYCDOT CAR | 20248520371-02 | 2025-04-01 | Failed to repair CAR #2048520371-01 | Dover St b/w Hampton Ave & Oriental Blvd | BED819 | 40 | 40 | N/A
NYCDOT CAR | 20250720007-01 | 2025-02-04 | Temp sewer trench overdue for final restoration | 137 Rd & 218 St | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20250720008-01 | 2025-02-04 | Temp sewer trench overdue for final restoration | 137 Rd b/w 218 St & 219 St | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20250720009-01 | 2025-02-04 | Temp sewer trench overdue for final restoration | 137 Rd & 219 St | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20250720010-01 | 2025-02-04 | Temp sewer trench overdue for final restoration | 219 St b/w 137 Rd & 138 Ave | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20250720011-01 | 2025-02-04 | Temp sewer trench overdue for final restoration | 219 St b/w 137 Rd & 1337 Ave | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20256270025-01 | 2025-02-05 | Temp sewer trench overdue for final restoration | 212 Pl b/W 104 Rd & Hollis Ave | SEQS24 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-11 | 40
NYCDOT CAR | 20256270076-01 | 2025-04-22 | Portion of curb damaged IFO 212-26 113th Ave | 113 Ave b/w 212 St & Delevan St | SEQS24 | 40 | 40 | N/A | Closed | Protested. Protest accepted 5/2/2025 | 0 | 2025-05-02 | 0
NYCDOT CAR | 20256460001-01 | 2025-03-10 | Restore "STOP" lane markings. Apply IBM color code year 2025 | 664 Camberleng b/w E. 188 St & E. 189 St | LSLRPBX2 | 40 | 40 | N/A | Closed | paid | 40 | 2025-03-10 | 40
NYCDOT CAR | 20258520089-01 | 2025-04-03 | Temp restoration needs made permanent. IFO #152 Amherst Ave | Amhers St b/w Hampton Ave & Oriental Blvd | BED819 | 40 | 40 | N/A |  | Protest Pending
NYCDOT CAR | 20258520131-01 | 2025-05-01 | Water valve cover popped up, tripping hazard. IFO 179 Beaumont St | Beaumont St b/w Hampton Ave & Oriental Blvd | BED819 | 40 | 40 | N/A |  | Protest Pending
NYCDOT CAR | 20258580134-01 | 2025-05-29 | Color code missing from permanent water restoration. Color code is needed | Cambreleng Ave b/w E 188 St & E 189 St | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580136-01 | 2025-05-29 | Permanent restoration missing color code IFO 2471 and 2481 | 2498 Cambreleng Ave b/w E 189 St & East Fordham Rd | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580137-01 | 2025-05-29 | Color code missing from permanent water restoration. Color code is needed | 2414 Hoffman St b/w E 187 St & E 188 St | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580138-01 | 2025-05-29 | Missing color code from permanent restoration & expansion joint IFO 2410 . Color code and expansion joint are needed | 2410 Hoffman St b/w E 187 St & E 188 St | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258480144-01 | 2025-05-30 | Permanent restoration missing color code IFO 2477. Color code needed | 2477 Cambreleng Ave b/w E 189 St & East Fordham Rd | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258480145-01 | 2025-05-30 | Permanent restoration missing color code and expansion joints need to be fully filled and sealed IFO 2378 | 2378 Hughes Ave b/w E 186 St & E 187 St | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580147-01 | 2025-05-31 | Permanent restoration missing color code and expansion joints need to be fully filled and sealed IFO 648 | 648 E 183 St b/w Belmont Ave & Hughes Ave | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580148-01 | 2025-05-31 | Permanent restoration missing color code and expansion joints need to be fully filled and sealed IFO 651 | 655 E 183 St b/w Belmont Ave & Hughes Ave | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/2/2025 | 0 | 2025-06-02 | 0
NYCDOT CAR | 20258580149-01 | 2025-05-31 | Permanent restoration missing color code and expansion joints need to be fully filled and sealed IFO 2261 | 2276 Hughes Ave b/w Crescent Ave & E 183 St | LSLRPBX2 | 40 | 40 | N/A | Closed | Protested. Protest accepted 6/4/2025 | 0 | 2025-06-04 | 0
| 20254560036-01 | 2025-07-29 | Broken valve cover IFO 2378 Hughes Ave | 2378 Hughes Ave | LSLRPBX2 | 40 | 40 | N/A | Open | Protest Denied
| 20254560036-02 | 2025-09-23 | Broken valve cover IFO 2378 Hughes Ave | 2378 Hughes Ave | LSLRPBX2 | 40 | 40 | N/A | Open
| 20254560036-03 | 2025-11-01 | Broken valve cover IFO 2378 Hughes Ave | 2378 Hughes Ave | LSLRPBX2 | 40 | 40 | N/A | Open
| 20251700245-01 | 2025-10-29 | Permanent sewer trench sunken 2" in localized area | IFO 81-04 242 St, Queens | SEQS24 | 40 | 40 | N/A | Open